## Slide 1
HMD PROJECT — STATUS PRESENTATION
Hot Metal Distribution System
End-to-end project review — design, development, integration, current state, path forward
PREPARED FOR
JSW Steel Limited — Vijayanagar Works
PREPARED BY
Deevia Software (India) Pvt. Ltd. — 14 May 2026

## Slide 2
SECTION — · OVERVIEW
Agenda
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
2
A. Project Foundation
  Goal, scope, system architecture
B. Project Timeline
  Original plan vs actual progress
C. Infrastructure & Server Setup
  Hardware, network, software stack
D. Data Sources & Integration
  Three external sources, integration dates
E. Application Capabilities
  Module-by-module walkthrough
F. Current Operations Status
  What's live, what's verified
G. Data Reality / Findings
  What's reliable, what isn't, key gaps
H. Clarifications Needed from JSW
I. Path Forward + J. Close

## Slide 3
SECTION A · PROJECT FOUNDATION
Project goal and scope
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
3
THE OPERATIONAL CHALLENGE
JSW Vijayanagar Works operates a hot metal distribution network connecting 7 producers (BF1–BF5, COREX1, COREX2) to 4 steel melting shops (SMS-1 through SMS-4) using a fleet of 53 torpedo ladles.
Coordinating torpedo allocation, trip planning, real-time tracking, and per-trip lifecycle management across the network is operationally complex and currently relies on disparate sources of data without a unified planning or monitoring layer.
WHAT HMD DELIVERS
Centralised real-time view of every torpedo and every trip
Role-based access for Admin, Producer, Consumer operators
Daily and monthly planning with optimisation (PuLP) for route assignment
Trip lifecycle management — 16 distinct states from creation to completion
Per-node operations monitoring, deviation analytics, and KPI dashboards
Audit trail, alerts, reporting (PDF/Excel), and maintenance scheduling
Integration with JSW source systems — torpedo GPS, BF weighbridge transactions, SMS hot-metal receipts

## Slide 4
SECTION A · PROJECT FOUNDATION
System architecture
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
4
HMD ARCHITECTURE — A SINGLE WEB APPLICATION INTEGRATING THREE JSW DATA SOURCES
USERS — JSW operators (Admin / Producer / Consumer roles) via web browser over JSW network
HMD APPLICATION — running on BF4 PC (JSW network)
• Frontend (React + Vite) — Dashboard, Trip Mgmt, Planning, Operations, Statistics, Reports, Audit, Fleet, Maintenance, Settings
• Backend (FastAPI + Python) — REST API, RBAC, JWT auth, audit trail, alert detector, optimisation engine, scheduled syncs (APScheduler)
• Local storage (PostgreSQL + Redis) — application state, mirrors of upstream data, fleet & trip records, configs
SuVeechi MySQL
Real-time torpedo GPS
• vw_unit_status_ist • 53 torpedoes • 10-second refresh • Live since 06-May-2026
WBATNGL Oracle
BF weighbridge transactions
• BF3 + BF5 schemas • 8 of 9 views working • 60-second sync • Trip mirror since 08-May-2026
HTS Oracle
SMS hot-metal heats
• VW_HTS_HOTMETAL_DATA • JVMLPROD instance • 5-minute sync • Access set up 11-May-2026

## Slide 5
SECTION B
Project Timeline
Original plan, actual progress, and where we stand today.

## Slide 6
SECTION B · PROJECT TIMELINE
Original plan — five milestones, Dec 2025 to Aug 2026
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
6
ID | Milestone | Start Date | End Date | Status as of 14-May-2026
M1 | Requirements Collection & Design | 08-Dec-2025 | 15-Jan-2026 | Complete
M2 | Core HMD Development | 15-Jan-2026 | 22-May-2026 | 98% — Active
M3 | Dashboard & Integration | 15-Apr-2026 | 19-Jun-2026 | 65% — Active
M4 | Testing Simulation & Pilot | 26-Jun-2026 | 24-Jul-2026 | Not Started
M5 | Full Go-Live & Stabilization | 24-Jul-2026 | 07-Aug-2026 | Not Started
KEY POINTS
M1 closed on schedule — requirements, hardware spec, queries baseline established.
M2 is 98% complete — the core HMD application has shipped; remaining 2% reserved for refinements after live-data observation.
M3 (Dashboard & Integration) was blocked until April 2026 due to network and database access; now actively progressing after VPN granted 06-May-2026.
M4 and M5 are downstream of M3 — start dates were shifted +1 week as per Weekly Report 12 (23-Apr-2026).

## Slide 7
SECTION B · PROJECT TIMELINE
What actually happened — major events on the journey
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
7
Date | Event
Dec-2025 | Project kickoff — Queries shared with JSW, hardware spec submitted (HPE ProLiant DL160 Gen9 + Windows Server 2022)
Jan-2026 | Historical data received from JSW — 1-year torpedo loading, cycle time report, weighbridge report, maintenance reports
Jan–Apr 2026 | Core development — 216 backend + frontend tasks completed across all V7 modules
Feb-2026 | Windows Server 2022 license procured
Mar-Apr 2026 | Data requirements iteration with JSW IT — 3 source-system access requests, multiple Teams meetings
02-Apr-2026 | SuVeechi MySQL view shared by vendor (Ganesha)
08-Apr-2026 | Network access escalation — 100% packet loss to JSW DB servers; root cause traced to absent LAN
14-Apr-2026 | Formal approvals closed — Gagan Chopra approval forwarded; DEP008 closed
~30-Apr-2026 | HMD PC physically integrated into JSW network — placed at BF4
06-May-2026 | VPN access granted to Deevia team — DEP009 + DEP012 closed; SuVeechi sync went LIVE — 53 torpedoes streaming GPS every 10s
07-May-2026 | Live Tracking Phase 1–3 shipped — map polish, Torpedo Drawer, per-torpedo capacity backfill
08-May-2026 | WBATNGL Trip Mirror sprint shipped — 60-second sync, BF-side trip data flowing into HMD
11-May-2026 | Oracle HTS connectivity unblocked — service name + user identified; DEP007 closed

## Slide 8
SECTION B · PROJECT TIMELINE
Current milestone position — M2 nearly closed, M3 active, M4-M5 ahead
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
8
ID | Milestone | Planned | Actual | Comment
M1 | Requirements & Design | 100% | 100% | Complete
M2 | Core Development | 100% (planned) | 98% | On Track
M3 | Dashboard & Integration | 65% (planned) | 65% | On Track — major jump in May
M4 | Testing & Pilot | 0% | 0% | Awaiting M3 completion
M5 | Go-Live & Stabilization | 0% | 0% | Awaiting M4 completion
OVERALL POSITION (14-May-2026)
Overall project progress: approximately 53% complete against the planned timeline.
M3 made a substantial jump in early May (from ~18% to 65%) as VPN access enabled remote testing of all three source databases.
Remaining 35% of M3 depends on: (a) Level 1/2 production signals (DEP002, overdue), (b) Production/Consumption rules documentation (DEP005, overdue), (c) end-to-end pilot validation against real plant operations.
M4 (Testing) and M5 (Go-Live) are tracking start dates of 26-Jun-2026 and 24-Jul-2026 respectively, contingent on M3 completion.

## Slide 9
SECTION C
Infrastructure & Server Setup
Hardware, network, and software stack for HMD at JSW Vijayanagar.

## Slide 10
SECTION C · INFRASTRUCTURE & SERVER SETUP
Server topology and physical deployment
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
10
HMD HOST SERVER (AT JSW BF4 LOCATION)
Specification | Detail
Hardware | HPE ProLiant DL160 Gen9
Operating System | Windows Server 2022 (license procured Feb-2026)
Application Stack | FastAPI · React · PostgreSQL · Redis
Runtime | Python venv + Node.js + nginx (frontend)
Physical Location | BF4 (Blast Furnace 4 area)
Owned & Maintained by | JSW BF4 team (per 22-Apr-2026 agreement)
ACCESS & CONNECTIVITY
Aspect | Detail
Frontend access | http://<BF4-PC>:5173 (JSW intranet)
Backend API | http://<BF4-PC>:8000
Database (internal) | PostgreSQL on localhost:5432
Cache (internal) | Redis on localhost:6379
Remote development | VPN to JSW network → AnyDesk to BF4 PC
Source DB access | Outbound to JSW DB servers (SuVeechi 3306, Oracle 1522)
KEY POINT
The HMD application lives entirely inside JSW's secure network. No data leaves the plant. All three source databases (SuVeechi, WBATNGL, HTS) are reached from the BF4 PC over JSW's internal network. Deevia developers connect via approved VPN credentials (granted 06-May-2026) for ongoing support and updates only — no production data flows outside JSW infrastructure.

## Slide 11
SECTION C · INFRASTRUCTURE & SERVER SETUP
Network integration journey
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
11
Date | Network Integration Event
Mar-2026 | Initial network plan — Deevia dev system to be placed at BF4-L2 subnet (192.168.150.100)
08-Apr-2026 | Network access request raised — DB servers unreachable from Deevia PC (100% packet loss)
17-Apr-2026 | Root cause confirmed — no LAN connection from DSI laptop (firewall ruled out)
21-Apr-2026 | Teams meeting with JSW IT (Divakara, Hari, Pradeep, Vasagerappa) to resolve LAN integration approach
22-Apr-2026 | Server hardware maintenance ownership agreed with BF4 team (Divakar's email)
~24–30-Apr-2026 | PC physically delivered to JSW IT, integrated into BF4 network, returned operational
~30-Apr-2026 | BF4 LAN connectivity verified — all 3 DB servers reachable from BF4 PC
06-May-2026 | VPN access for Deevia team granted (Vamsi Krishna obtained domain ID from 365 Support; Raghavendra/JSW IT configured VPN). DEP009 + DEP012 both closed.
OUTCOME
By 06-May-2026, the BF4 PC was reachable from Deevia development laptops over JSW VPN, and outbound connectivity to all three source databases was operational. This was the single biggest unblocking event of M3 — within two days of access, both SuVeechi and WBATNGL syncs went live.

## Slide 12
SECTION C · INFRASTRUCTURE & SERVER SETUP
Software stack and security posture
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
12
APPLICATION STACK — STANDARD ENTERPRISE WEB APPLICATION
PRESENTATION
React 19 + Vite 7 + React Router v7 — single-page web app, role-based UI, TypeScript-incremental. Charts: Recharts. Maps: Leaflet. PDF/Excel export: jsPDF, xlsx.
APPLICATION
FastAPI + Uvicorn — async REST API. 13 SQLAlchemy ORM models. APScheduler for background syncs. Optimisation: PuLP (linear programming for daily plan generation). Tracing: OpenTelemetry.
DATA
PostgreSQL (primary). Redis (cache with in-memory fallback). Alembic-managed schema migrations. Local mirrors of SuVeechi / WBATNGL / HTS for resilient analytics.
SECURITY
JWT authentication. bcrypt password hashing. RBAC (Admin / Producer / Consumer). Account lockout, rate limiting, CSRF protection, audit trail with username + IP.

## Slide 13
SECTION D
Data Sources & Integration Journey
Three external sources of truth, integrated into HMD over April–May 2026.

## Slide 14
SECTION D · DATA SOURCES & INTEGRATION
Three external sources — at a glance
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
14
Source | Engine | Primary view | What it provides | Sync rate | Status
SuVeechi | MySQL | vw_unit_status_ist | 53 torpedoes — live GPS, status, location | 10 seconds | Live since 06-May
WBATNGL | Oracle | BF3 + BF5 schemas (9 views) | BF-side weighbridge transactions, tap data, chemistry | 60 seconds | Live since 08-May
HTS | Oracle | VW_HTS_HOTMETAL_DATA + 4 tables | SMS hot-metal receipts, caster events (SMS-4) | 5 minutes | Access set up 11-May
HOW THESE SOURCES MAP TO THE BUSINESS
SuVeechi — answers "where is each torpedo right now". Drives the live map and the live trip view.
WBATNGL — answers "what was tapped, weighed, and dispatched from the BF side". Drives producer-side reporting.
HTS — answers "what was received at the converter and what heat was made". Drives consumer-side reporting.
Each source is owned by a different JSW team (SuVeechi vendor for GPS; BF Operations for WBATNGL; SMS IT for HTS).

## Slide 15
SECTION D · DATA SOURCES & INTEGRATION
How each source was unblocked — dates and owners
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
15
Date (2026) | Event
17-Mar | HMD Data Requirement Sheet shared with Gagan Chopra
23-Mar | Pritam Saha sets up Torpedo data clarification meeting
25-Mar | Updated Data Requirements re-shared after meeting
31-Mar | Gagan Chopra approves SuVeechi integration path
02-Apr | SuVeechi MySQL view (vw_unit_status_ist) shared by Ganesha (vendor)
03-Apr | Oracle HTS view credentials shared by Hari Prasad (JSW IT)
14-Apr | DEP008 closed — Gagan approval propagated; remaining Oracle accesses cleared
16-Apr | Oracle WBATNGL 3rd view shared by Kotaiah (JSW DBA)
06-May | VPN access granted (DEP012 closed); SuVeechi sync live; WBATNGL sync verified
08-May | WBATNGL trip mirror sprint shipped; per-torpedo capacity backfilled
11-May | HTS connectivity unblocked; correct service name + user identified; DEP007 closed
Five distinct JSW teams contributed to the integration — Production (Irfan, Gagan), IT Infrastructure (Divakar, Vasagerappa, Pradeep), Oracle DBA (Kotaiah), SMS IT (Hari Prasad), and the SuVeechi vendor (Ganesha, Sanjay). Coordination was the critical-path constraint, not engineering.

## Slide 16
SECTION D · DATA SOURCES & INTEGRATION
What each source provides — table view
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
16
Source | Fields provided
SuVeechi (MySQL) | Torpedo identifier (`unitname`) Latitude / Longitude Status (Idle / Moving / Ign Off) Plant location (free text) Report timestamp
WBATNGL (Oracle) | Trip identifier Torpedo (`LADLENO`) Producer (`SOURCE_LAB`) Weighbridge weights (tare, gross, net) Tap data (tap_no, tap_hole, temp, S, Si) Lifecycle timestamps (first_tare, closetime, out_date, sms_ack)
HTS (Oracle) | Heat identifier (`HEAT_NO`) Converter (D/E/F/G/H/I) and SMS unit Torpedo arrival/release time Hot-metal quantity received Caster heat process events (SMS-4 only) Consumption / yield data (SMS-4 only)

## Slide 17
SECTION D · DATA SOURCES & INTEGRATION
Local HMD database — what HMD stores
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
17
WHY HMD MAINTAINS LOCAL MIRRORS OF EXTERNAL SOURCES
Resilience — if any source database is briefly unreachable, HMD continues to operate from its local mirror.
Performance — HMD-side queries (dashboards, reports) hit local PostgreSQL with sub-second response, not the source.
Reduced load on JSW source systems — HMD pulls deltas at controlled intervals (10s / 60s / 5min) rather than per-user.
Application-owned state stays on HMD side — user accounts, alerts, audit trail, configuration, fleet master, planning data.
WHAT'S STORED LOCALLY
Category | Contents
Application state | Users, roles, settings, system configuration, alerts, audit log
Fleet & nodes | 53 torpedoes (master), plant nodes, weighbridges, converters
Planning & trips | Daily plans, distribution assignments, trip lifecycle records, route configurations
Mirrors of source data | fleet_live_locations (SuVeechi snapshot), wbatngl_trip_mirror, hts_heat_mirror + caster mirrors

## Slide 18
SECTION E
Application Capabilities
V7 — the production-ready Hot Metal Distribution application.

## Slide 19
SECTION E · APPLICATION CAPABILITIES — V7
Module overview — 12 functional areas
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
19
Dashboard
KPI overview, alerts summary
Trip Management
16-state lifecycle, manual & assigned trips
Live Tracking
Real-time torpedo map, status, current trip
Operations
Per-node operator view (Producer / Consumer)
Daily Planning
Capacity, distribution, daily routes
Strategic Planning
Monthly plan, HM Matrix, optimization
Torpedo Management
Fleet registry, status, capacity, lifecycle
Maintenance Scheduling
Calendar view, overlap prevention
Statistics
KPIs, throughput, deviation analytics
Reports
PDF / Excel / CSV exports, 10+ report types
Audit Trail
Username, IP, change diff, regulatory log
Settings & Admin
Users, roles, configurations
All 12 modules are role-aware. Admin sees everything; Producer / Consumer see their node-relevant views only.

## Slide 20
SECTION E · APPLICATION CAPABILITIES — V7
Trip lifecycle management — 16 states from creation to completion
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
20
0
Pending
1
Assigned
2
WB Tare Entry
3
WB Tare Recorded
4
Producer Entered
5
Loading Started
6
Loading Ended
7
Producer Exited
8
WB Gross Entry
9
WB Gross Recorded
10
Consumer Entered
11
Unloading Started
12
Unloading Ended
13
Completed
14
Canceled
15
Aborted
FEATURES
Status transitions are validated server-side — invalid jumps blocked by a state-machine.
Each transition is timestamped and audit-logged with the user who performed it.
Live deviation tracking compares expected times (from HM Matrix) against actuals; threshold alerts fire at 10, 20, 30 minute deltas.
Trips can be created automatically by the assignment engine, manually by Admin, or auto-detected from upstream weighbridge data (WBATNGL mirror).
Trip cancellation is governed by role permissions; abortion mid-execution requires admin override.

## Slide 21
SECTION E · APPLICATION CAPABILITIES — V7
Planning — daily, monthly, and optimised distribution
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
21
DAILY PLANNING
Per-day capacity entry by Producer / Consumer roles
Status workflow: Primary → Revised → Confirmed
Auto-computed daily plan rolls into monthly view
Cache-backed for instant operator response
MONTHLY / STRATEGIC PLANNING
Admin-only monthly capacity calendar
Five planning tabs: Executive, Configuration, Maintenance, Strategic, Weighbridge
Distribution Assignment with Committed / Proposed / Superseded states
Historical comparison and forecast view
HM MATRIX & OPTIMISATION
Hot-Metal Matrix — bidirectional travel time table per producer-consumer pair
Fill, Unload, Wait time configuration per node
Linear-programming optimiser (PuLP) generates day-optimal allocation
Optimisation considers: capacity, distance, dwell, queue, and torpedo availability

## Slide 22
SECTION E · APPLICATION CAPABILITIES — V7
Operations · Statistics · Deviation Analytics
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
22
OPERATIONS
Real-time node-specific control surface
Per-producer and per-consumer dashboards
Admin sees tabbed view across all producers / consumers
Live status of each node, current torpedo, in-progress trips
Configurable thresholds — warning (10 min), alert (20 min), critical (30 min)
Trip-stage progression with phase-level deviation tracking
STATISTICS
Multi-dimensional KPI dashboard
Producer-specific, Consumer-specific, and global views
Headline KPIs: trips today, tonnes today, average cycle, on-time %
Throughput trends (hourly / daily / monthly)
Fleet utilisation, torpedo cycle distribution, route comparison
All filtered by date range, producer, consumer, or grade
DEVIATION ANALYTICS
Six analytical lenses on schedule adherence
Deviation summary by category (Early / On-Time / Warning / Alert / Critical)
By node — per-producer and per-consumer breakdown
By phase — Loading / Transit / Unloading split
Trends — daily and monthly time-series
Period-over-period comparison
Root cause analysis: shift, day-of-week, worst routes

## Slide 23
SECTION E · APPLICATION CAPABILITIES — V7
Live Tracking · Torpedo Management · Maintenance
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
23
LIVE TRACKING
Real-time map of every torpedo's position
Leaflet-based interactive map of plant area
53 torpedoes shown with status-coloured markers (Idle / Moving / Ign Off)
Click any torpedo → Torpedo Drawer slides in with:
• Live latitude / longitude and last update time
• Current trip details + recent trip history
• Per-torpedo capacity (from WBATNGL backfill)
• Maintenance schedule and ladle attributes
TORPEDO MANAGEMENT
Fleet registry — 53 torpedoes
Master list of every torpedo (TLC-01 through TLC-53)
Status workflow: Operating / Maintenance / Moving
Per-torpedo capacity (range observed: 425–485 MT)
Capacity auto-refreshed nightly from WBATNGL historical weighbridge data
Soft-delete (retired torpedoes preserved for audit)
MAINTENANCE SCHEDULING
Calendar-based maintenance planning
Schedule maintenance windows per node or torpedo
Overlap prevention to avoid scheduling conflicts
Status tracking: Ongoing / Scheduled / Completed
Modal-based create / edit with role permissions
Duration auto-calculated

## Slide 24
SECTION E · APPLICATION CAPABILITIES — V7
Reports · Audit Trail · Settings & Security
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
24
REPORTS
10+ predefined report types — trip history, planning vs actual, deviation summary, fleet utilisation, throughput, etc.
Export formats: PDF (with branding), Excel, CSV
Filterable by date range, producer, consumer, grade, role
Scheduled reports with history retention
Saved-report configurations for repeat exports
AUDIT TRAIL
Every action by every user logged
Username, IP address, user agent, action, before/after diff
Filterable, searchable, exportable
Atomic / transaction-safe with retry logic
Regulatory compliance posture
SETTINGS & ADMIN
User management — create, role-assign, lock, unlock, soft-delete
System configuration — travel times, fill times, wait times, default capacities
Deviation threshold configuration
Notification preferences
Centralised admin control panel
SECURITY POSTURE
JWT authentication with 480-min token expiry (configurable)
bcrypt password hashing
Account lockout after 5 failed attempts (15-min window)
CSRF protection (double-submit cookie pattern)
Rate limiting (tiered: auth, high, medium, low)
Security headers (X-Content-Type-Options, CSP, etc.)

## Slide 25
SECTION F
Current Operations Status
What's live today, what data is flowing, and what's been verified end-to-end.

## Slide 26
SECTION F · CURRENT OPERATIONS STATUS
What's running on the BF4 PC today
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
26
Service / Job | Frequency | Status | Notes
HMD backend (FastAPI) | Port 8000 | Running | Always-on; service-managed
HMD frontend (React) | Port 5173 (dev) / built static | Running | Served to JSW intranet browsers
PostgreSQL | Port 5432 (localhost) | Running | Local DB for HMD application state + source mirrors
Redis | Port 6379 (localhost) | Running | Cache; auto-fallback to in-memory if unavailable
SuVeechi sync job | Every 10 seconds | Live | 53 torpedoes — GPS + status snapshot
WBATNGL trip sync job | Every 60 seconds | Live | BF-side trip transactions
HTS sync job | Every 5 minutes | Live | SMS-side heat records (recently established)
WBATNGL capacity backfill | Daily at 03:00 IST | Live | Refreshes per-torpedo capacity from historical net weights

## Slide 27
SECTION F · CURRENT OPERATIONS STATUS
Live data flowing into HMD
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
27
SuVeechi GPS
53
torpedoes streaming
Refreshed every 10 seconds. Delivers latitude, longitude, ignition status, and free-text plant location for every active torpedo.
WBATNGL trips
~3,300
trip records / 30 days
BF3 + BF5 schemas, union view BF3.WB_TRANS_DATA_ITRO. Daily volume: tens to hundreds of trips, depending on production rate.
HTS heats
~35,000
heat records (historical)
Full 10-year history available; current rate steady. SMS-2 and SMS-4 converters represented.
OBSERVATIONS
Data flow is steady. No source has gone offline since the integration went live in early May.
The HMD application's dashboard refreshes automatically as new data arrives — no manual refresh required.
Local mirrors mean operators see sub-second response times even when the underlying source is slow.
Per-torpedo capacities were backfilled from WBATNGL historical data (replacing the 360-MT default with real ranges between 425–485 MT).

## Slide 28
SECTION F · CURRENT OPERATIONS STATUS
End-to-end verification on the BF4 PC
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
28
VERIFIED FLOWS (AS OF 14-MAY-2026)
Flow | Status | Notes
Torpedo GPS → live map | Verified | Source torpedo position appears on HMD map within ~10 seconds of update
Trip dispatched (BF) → HMD record | Verified | New row in BF3.WB_TRANS_DATA_ITRO appears in wbatngl_trip_mirror within 60 seconds
Heat at SMS → HMD record | Verified | New heat in HTS appears in hts_heat_mirror within 5 minutes
Per-torpedo capacity refresh | Verified | Nightly 03:00 IST job runs; capacities updated from historical net weights
Trip lifecycle update → audit trail | Verified | Every transition logged with user, IP, before/after
Role-based access enforcement | Verified | Admin / Producer / Consumer routes correctly restrict views and actions
Backup of local DB | Pending | Backup schedule to be agreed with JSW IT once go-live is set

## Slide 29
SECTION G
Data Reality
What's reliable, what isn't, and the gaps that must be closed at source.

## Slide 30
SECTION G · DATA REALITY
Module status matrix — what works on current data
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
30
Module | Status | Reason
Trip lifecycle tracking | Functional with gaps | Producer side reliable; consumer-side acknowledgement inconsistent
Producer-side data (BF / COREX) | Functional with gaps | All 7 producers visible; Si chemistry only BF4; S anomalies non-BF4
Consumer-side data (all 4 SMS) | Partially blocked | SMS-2 and SMS-4 visible; SMS-1 and SMS-3 not represented
Fleet management (53 torpedoes) | Functional with inconsistencies | Fleet count discrepancy (HMD 53 vs HTS master 36)
Live positioning (GPS) | Functional with reliability gaps | Coverage complete; vendor-side telemetry limited
Geofencing / plant nodes | Partially blocked | No polygons available; node master list informal
Weighbridge audit | Functional with gaps | 3 weighbridges inferred; no calibration history
BF-side equipment downtime | Blocked | No source for producer-side downtime events
Production planning / targets | Blocked | No source for plans / targets / schedules
SMS performance (yield / loss) | Partially blocked | SMS-4 only; SMS-1/2/3 caster data not accessible
Heat trace (BF → SMS lineage) | Approximate | No shared identifier; time-window join only
Alerts & exceptions | Functional | Detector running; coverage tracks upstream data availability

## Slide 31
SECTION G · DATA REALITY
Key data findings — what JSW source data is missing or inconsistent
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
31
# | Finding | Implication
1 | Geofence polygons | No source provides plant-node geofences. SuVeechi vendor likely has them internally but does not expose. Required for boundary-sensitive events (entry/exit, dwell time).
2 | SMS-1 / SMS-3 absent | HTS contains heat records only for SMS-2 and SMS-4. SMS-1 not represented at all; SMS-3 likely uses EAF (out of scope for hot metal). Status confirmation needed.
3 | BF3 silent since 24-Sep-2025 | Zero trip activity recorded for BF3 in the past ~232 days. No source explains whether decommissioned, under refractory campaign, or temporarily idle.
4 | Si chemistry BF4-only | Of seven producers, only BF4 has silicon (Si) values populated. The other six producers report Si as NULL. Plant-wide Si specification cannot be enforced.
5 | Sulfur (S) values inconsistent | BF4 S values fall in plausible 0.015–0.050 band; non-BF4 values reach up to 2.83. Indicates unit or scale inconsistency at source.
6 | Producer-side downtime missing | HTS has equipment breakdown data for SMS side. No equivalent table exists or is exposed for any of the 7 producers.
7 | Production targets unavailable | No source database contains daily, monthly, or shift-level production targets. Every 'vs plan' comparison is structurally blocked.
8 | WBATNGL acknowledgement gaps | SMS-side acknowledgement (SMS_ACK_TIME) is NULL on approximately 45% of trip records. Trip-completion semantics unclear.
9 | Heat-to-trip linking key absent | WBATNGL and HTS share only the torpedo identifier. No common HEAT_NO or TRIP_ID exists between the two systems.
10 | SMS-2 caster data not readable | Caster process and consumption data for SMS-2 converters (D, E, F, G) appears to be in SPT001A schema. The integration user does not have read access.

## Slide 32
SECTION G · DATA REALITY
Operational implications — what these gaps block
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
32
Operational area | Status given current data
Production verification | Producer-side trips visible (all 7 BFs+COREX); consumer-side only for SMS-2/4. Comparing 'produced vs consumed' is feasible for the visible flow but incomplete plant-wide.
Real-time torpedo location | GPS streaming is reliable. Boundary detection (torpedo entered SMS-4 at HH:MM) is currently inferential — geofences from SuVeechi vendor would make it deterministic.
Yield and loss analytics | Available for SMS-4 only. Approximately 95% of plant heats run on SMS-2 — their yield, loss, and operator notes are not visible. SPT001A access would unlock this.
Plan-vs-actual reporting | No targets means no variance reports. The dashboards report absolute throughput but cannot show 'X% of daily plan achieved'.
Cause-and-effect analysis | Production drops observed in data have no corresponding cause records. The 'why' must come from operations team interviews rather than source data.
Plant-wide chemistry compliance | Si bounds enforceable only on BF4 trips. S anomalies on non-BF4 sources prevent uniform sulfur-spec alerting.

## Slide 33
SECTION G · DATA REALITY
A formal Data Gap Analysis report has been prepared
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
33
REPORT — HMD ↔ JSW DATA GAP ANALYSIS (V1.0)
A detailed companion document inventories every data requirement of the HMD system, contrasts it with what JSW currently provides across four source systems, and identifies every gap — missing, inconsistent, or fragmented — that prevents the system from operating on reliable, deterministic data.
Aspect | Detail
Coverage | 13 operational modules across 4 thematic clusters
Findings | 30 distinct data gaps + 5 cross-references
Severity breakdown | 7 BLOCKER · 17 SIGNIFICANT · 5 INCONSISTENT · 1 ENHANCEMENT
Per-gap content | 9-field summary + technical detail + sample data + verification SQL
Owner tagging | Each gap routed to: JSW IT / JSW Operations / JSW Planning / Vendor
Companion document | Available as a separate PDF for technical review
The Data Gap Analysis document is grounded in direct schema inspection and concrete query evidence collected during May 2026. It is structured to be acted on per gap by JSW IT, JSW Operations, and JSW Planning.

## Slide 34
SECTION H
Clarifications Needed from JSW
Specific items where Deevia requires confirmation or input to proceed.

## Slide 35
SECTION H · CLARIFICATIONS NEEDED FROM JSW
1. End-user identification and engagement
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
35
WHAT WE NEED
Identification of the day-to-day operators of the HMD system at JSW.
A working session with those end users to understand how they perform hot-metal distribution today — current tools, current pain points, current decision flow.
Their input on which HMD features map best to their current operational practice — and which features need adaptation.
WHY THIS MATTERS
The application is built to specification, but field-level usability depends on operator workflow.
End-user sessions surface details that data alone cannot — for example, what fields operators actually fill in during a shift versus what stays blank, and which decisions are made on-screen versus from a printed sheet.
Early engagement also derisks the pilot phase (M4): a system trained operators can use confidently goes live more smoothly.

## Slide 36
SECTION H · CLARIFICATIONS NEEDED FROM JSW
2. Production verification approach
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
36
PROPOSED APPROACH
Use trip data from both the producer side (WBATNGL) and the consumer side (HTS) as the primary signal for what was actually produced and consumed during a shift, day, or month.
Producer-side: sum of net-weight tonnes per producer over a period (covering all 7 BFs/COREX).
Consumer-side: sum of hot-metal-quantity tonnes received per converter over the same period (covering SMS-2 and SMS-4 with current access; SMS-1 / SMS-3 / SMS-2 caster pending JSW input).
Any persistent discrepancy between producer and consumer totals would be the operational signal — slag carryback, route losses, weighing drift, or missing nodes.
CONFIRMATION REQUESTED
Is this approach aligned with JSW's current production-reporting methodology, or is there a different reconciliation method in use today?
Who at JSW signs off on the daily / weekly / monthly production numbers, and what data sources do they use today?

## Slide 37
SECTION H · CLARIFICATIONS NEEDED FROM JSW
3. Geofencing — required for the live tracking module to function reliably
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
37
GEOFENCE POLYGONS ARE A MUST-HAVE — CURRENTLY NOT AVAILABLE FROM ANY SOURCE
WHAT IS NEEDED
Polygon coordinates (latitude/longitude vertex list) for every operational plant node — producers (BF1–BF5, COREX1, COREX2), consumers (SMS-1 through SMS-4), all weighbridges, intermediate yards, gates, and pouring stations.
A canonical list of every named plant node in use — including the intermediate locations that appear in SuVeechi tracking data (LRS1, LRS2, SMS2 North PS, HMY1 PCM, BF4 Entry, EY-AVTC Gate, SY-Track Hopper, etc.).
Each node's role classification — producer / consumer / weighbridge / yard / intermediate / gate.
WHERE TO GET THESE
Most likely already maintained internally by the SuVeechi vendor (the location-text strings in their feed are evidence of internal geofences).
Alternatively, JSW Operations could provide based on plant layout drawings — even rough polygons would be a significant improvement over single-point coordinates.
Once received, geofences will be loaded into HMD and used to derive deterministic entry/exit/dwell events for every torpedo.

## Slide 38
SECTION I
Path Forward
Open dependencies, next steps, and the completion forecast.

## Slide 39
SECTION I · PATH FORWARD
Pending dependencies and next steps
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
39
ID | Item | Owner | Status | Timeline
DEP002 | Level 1/2 production signals + Production Plan access | JSW Operations | Open · Overdue | Targeted: 30 days from this review
DEP005 | Production / Consumption rules documentation | JSW Operations | Open · Overdue | Targeted: 14 days from this review
DEP010 | BF5.WB_TRANS_DATA_ITRO Oracle view recompile | JSW | In Progress | Workaround in place; permanent fix pending
New | Geofence polygons for all plant nodes | SuVeechi vendor (via JSW) | New ask | Targeted: 30 days from this review
New | End-user identification + working session | JSW Operations | New ask | Within 14 days of this review — prerequisite for pilot phase

## Slide 40
SECTION I · PATH FORWARD
Completion forecast — M3, M4, M5 scenarios
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
40
ID | Milestone | Plan End | Best-case | Likely if delayed
M3 | Dashboard & Integration | 19-Jun-2026 | Same — if pending dependencies (DEP002, DEP005, geofence access) close within 30 days | Mid-Jul-2026 — if dependencies slip
M4 | Testing & Pilot | 24-Jul-2026 | Same — assuming M3 closes on plan and end-user availability confirmed | Aug-2026 — under slip scenario
M5 | Go-Live & Stabilization | 07-Aug-2026 | Same — pending successful pilot in M4 | Aug-Sep 2026 — under slip scenario
KEY MESSAGES
Engineering work for applicaiton is essentially complete. Remaining timeline is JSW-dependent — data exposure, operational confirmations, and end-user engagement.
If the eight pending items in the prior slide close on the targets shown, the original 07-Aug-2026 go-live remains achievable.
Each week of delay on JSW-side items shifts the go-live by approximately one week.
Deevia continues to maintain weekly status reports and is available for accelerated cadence (daily standups) during the pilot phase.

## Slide 41
SECTION J · CLOSE
Summary and discussion
HMD Project Status — Deevia Software for JSW Vijayanagar — 14 May 2026
41
PROJECT SUMMARY
HMD — full-featured hot metal distribution application — is built and operational on JSW infrastructure.
All three external data sources are integrated; data flows live every 10 seconds to 5 minutes.
Project tracking at approximately 53% completion overall, on plan for the 07-Aug-2026 go-live.
Outstanding items are predominantly JSW-side: data exposure, operational confirmations, and end-user engagement.
WHAT WE NEED FROM JSW
End-user identification and a working session — within 14 days.
Geofence polygons for all plant nodes — within 30 days.
Production targets / heat schedules / production-consumption rules — within 30 days.
SMS-2 caster data access (SPT001A) — within 30 days.
BF-side equipment downtime source — within 30 days.
DISCUSSION & Q&A